## Vendor Evaluation
Status Legend:
| Yes | Option Readily Available i.e. No development Required
| NO | Option not available and cannot be provided
| Development | Option will be provided after development
Timelines Days
S.No | Mobile Banking Features | Status | Additional Remarks by Inov8 | Compliance with SOW | Additional Remarks by JS Bank | Number of Transactions | Integration | Server | Mobile App | QA | Staging | SIT | UAT | Total
1 | Funds transfer (Own account FT, Inter Branch and Inter Bank,BLB) | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB FT Scenerios Prepaid to Credit Card Prepaid to BLB Prepaid to Prepaid Card Prepaid to Core/Debit Card Prepaid to IBFT Credit Card to Credit Card Credit Card to BLB Credit Card to Prepaid Card Credit Card to Core/Debit Card Credit Card to IBFT BLB to Credit Card BLB to BLB BLB to Prepaid Card BLB to Core/Debit Card BLB to IBFT Core to Credit Card Core to BLB Core to Prepaid Card Core to Core/Debit Card Core to IBFT | 36 CBS 1. Title Fetch 2. FT 3. IBFT Title Fetch 4. IBFT 5. BLB Title Fetch 6. BLB 7. FT Reversal 8. IBFT Reversal 9. BLB Reversal 10. Card Relationship Inquiry Credit Card 11. Title Fetch 12. FT 13. IBFT 14. BLB 15. FT Reversal 16. IBFT Reversal 17. BLB Reversal 18. Card Relationship Inquiry Prepaid Card 19. Title Fetch 20. FT 21. IBFT 22. BLB 23. FT Reversal 24. IBFT Reversal 25. BLB Reversal 26. Card Relationship Inquiry BLB Accounts 27. Account Relationship Inquiry 28. Title Fetch 29. IBFT 30. BLB 31. FT Reversal 32. IBFT Reversal 33. BLB Reversal 34. Card Relationship Inquiry 35. FT Debit Card 36. Card Relationship Inquiry | 30 | 12 | 30 | 25 | 10 | 30 | 10 | 147
2 | Utility payment | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB | 5 Bill Inquiry Bill Payment from Core/Debit Card Bill Payment from credit card Bill Payment from Prepaid card Bill Payment from BLB | 7 | 7 | 5 | 15 | 5 | 15 | 5 | 59
3 | Prepaid & postpaid payment | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB | Same as point 2
4 | Internet service provider payment | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB | Same as point 2
5 | Mobile Top up | Yes |  | Yes | already covered in point#3 | already covered in point#3
6 | Credit card bill payment | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB Scenarios: JSBL Credit Card 1 Link Credit Card | JSBL credit card payment will be handled with FT as mentioned in point# 1 1 Link Credit card payment will be handled via IBFT as mentioned in point#1 | 4 | 5 | 4 | 5 | 3 | 5 | 2 | 21
7 | ATM and Branch locator | Yes |  | Yes | Application front end Backend bank portal user to for configurations & management of new and existing branches | no integration required from middleware | 0 | 3 | 3 | 5 | 2 | 0 | 1 | 14
8 | Balance inquiry | Yes |  | Yes | Will be part of Account Summary Point # 49 | [8 empty] | 0
10 | Account statements | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Debit Card 3. Credit Card 4. Prepaid Card 5. BLB | 5 1. Core Banking Account Statement 2. Debit Card Statement 3. Credit Card Statement 4. Prepaid Card Statement 5. BLB Statement | 5 | 10 | 10 | 10 | 5 | 5 | 2 | 47
11 | Transaction History | Yes |  | No | Mobile Channel Activity | no integration required from middleware financial and non financial tranctions will show on mobile | 0 | 3 | 2 | 3 | 2 | 0 | 1 | 11
12 | Payment details (Remarks on FT) | Yes |  | Yes | Aditional Field in Fund Transfer for comments | Will be covered with additional field with point # 1 | [7 empty] | 0
13 | Cards PIN change and Internet password change | Yes |  | Yes | Cases: 1. Debit Card 2. Prepaid Card 3. Credit Card 4. Internet Password Transaction PIN/OTP valid for 15 minutes bank configurable | 4 1. Debit Card PIN Change 2. Prepaid Card PIN Change 3. Credit Card PIN Change 4. Internet password change | 7 | 6 | 3 | 5 | 3 | 5 | 1 | 30
14 | Favorite Beneficiaries | Yes |  | No | Cases: 1. Debit Card/Core Account 2. Prepaid Card 3. Credit Card 4. BLB | 8 1. Manage Debit Card/Core Account Beneficiaries 2. Manange Prepaid Card Beneficiaries 3. Manage Credit Card Beneficiaries 4. Manage BLB Beneficiaries 5. Get Debit Card/Core Account Beneficiaries 6. Get Prepaid Card Beneficiaries 7. Get Credit Card Beneficiaries 8. Get BLB Beneficiaries | 5 | [6 empty] | 5
15 | Favourite Billers | Yes |  | No |  | 2 1. Manage Bill Payment Beneficiaries 2. Get Bill Payment Beneficiaries | 3 | [6 empty] | 3
16 | Alerts (SMS & Email) | Yes |  | Yes | Backend Portal for Configure Alert (Email, SMS) for transaction (Financial, Non Financial). 1. Configurtion for alert for a transasction 2. Change content of alert | 2 1. Email sending via SMTP 2. Insert SMS in table or M3Tech SMS sending | 2 | [6 empty] | 2
17 | Social Media Integration | Yes |  | No | 1. Get Image of beneficiary on fund transfer if possible. 2. Send invite for download Mobile Application to friend list. 3. Share Transaction detial on Social Media Public/Private mode. 4. Get User profile detail from social media | No integration is required on middleware | 0 | [6 empty] | 0
18 | Ticketing for Cinema and Buses | Yes |  | No | JSBL Mobile App via account Payment transaction will be initiated through mobile app Middleware will send the advice to Falcn Pay system JSBL Mobile App via gift card Transaction will be processed between FP & JSBL MB App No integration required with middleware Falcon Pay via Account Payment transaction will be initiated through Falcon Pay app Falcon Pay App via gift card Transaction will be processed on Falcon PayApp No integration required with middleware | 5 JSBL Mobile App via account 1. Payment transaction 2. Reversal advice 3. Payment Advice Falcon Pay via Account 1. Payment transaction 2. Reversal advice | 5 | [6 empty] | 5
19 | Merchant Payments - Retail through NFC and QR | Yes |  | Yes | For QR code payment: JSBL Mobile App via account Payment transaction will be initiated through mobile app Middleware will send the advice to Falcn Pay system JSBL Mobile App via gift card Transaction will be processed between FP & JSBL MB App No integration required with middleware Falcon Pay via Account Payment transaction will be initiated through Falcon Pay app Falcon Pay App via gift card Transaction will be processed on Falcon PayApp No integration required with middleware For NFC Payments Final scope will be finalized by JSBL this will be covered in mobile app and telenor api required for finalization by Registration for NFC: 1. Login into App 2. Use Easypay NFC for payment 3. JS authenticates customer 4. Sends request to RPS with JS account, MSISDN, App code etc 5. RPS assigns EP NFC ID and binds to customer App Transaction through NFC: 1. Login into App 2. Customer selects option to pay via EP NFC 3. Tap. App transmits EP NFC ID 4. Terminal reads and merchants adds amounts and submits 5. Request lands on RPS. RPS routes to JS 6. JS authenticates transaction with TPIN on customer App 7. JS sends authentication and merchant slip is printed | same as point 18 for QR code only | 0 | [6 empty] | 0
20 | Digital Payments | Yes |  | No | JSBL Mobile App via account Payment transaction will be initiated through mobile app Middleware will send the advice to Falcn Pay system JSBL Mobile App via gift card Transaction will be processed between FP & JSBL MB App No integration required with middleware Falcon Pay via Account Payment transaction will be initiated through Falcon Pay app Falcon Pay App via gift card Transaction will be processed on Falcon PayApp No integration required with middleware | same as point 18 | 0 | [6 empty] | 0
21 | Gift cards Purchase and Top Up | Yes |  |  | JSBL Mobile App via account Payment transaction will be initiated through mobile app Middleware will send the advice to Falcn Pay system Falcon Pay via Account Payment transaction will be initiated through Falcon Pay app At Merchant Location via Cash If Only FalconPay Customer: Push transaction will be sent to FP via merchant If Falcon Pay & JSBL Mobile app customer: Push transaction will be sent to FP and JSBL Mobile app via merchant JSBL mobile app will share customer coordinates and device information JSBL mobile app will be able to pull card details from Falcon Pay system Purchased Gift cards through FP can be used at merchant location and website both without registration on FP & JSBL MB app by just using the card number and OTP | same as point 18 | 0 | [6 empty] | 0
22 | Location based services showing merchant outlets and corresponding Discounts | Yes |  | Yes ( ATM/Branches/Agents) | Mobile app will fetch merchant location via FalconPay customer Push notifications for JSBL MB app based on geofancing for deals and discounts will be sent by falcon pay platform JSBL mobile app will share customer coordinates and device information Ensure there is no duplication of notifications | No integration with middleware | 0 | [6 empty] | 0
23 | Biometric login | Yes | It is device specific and OS Specific 19.12.2016:Biometric based login will require a change in authentication mechanism at RDV / NIMBUS to allow for a secondary login type. Our price will cover this integration | Yes | 23.12.2016:JSBL: Agreed that will be used off of device, no integration required Customer CNIC, Mobile Number & emaill will be returend to JSBL MB app | 2 1. BVS authentication on middleware 2. BVS registration on middleware | 2 | [6 empty] | 2
24 | Login with Facebook | Yes | Can be provided, but for security reasons and by SBP regulations, Financial applications require a separate login 19.12.2016: It is Inov8 recommendations to drop this option due to security reasons and the amount of account mishaps that take place on Facebook | No | 23.12.2016: JSBL: Kazim (IT), we can remove login from facebook from the scope. | Out of scope | 0 | [6 empty] | 0
25 | Pay Order request | Yes |  | No | 1. Backend portal will enable user to confirgure the form fields 2. Mobile App will show this dynamic form to the user 3. Backend user can view submitted forms through reports 4. Email configuration for form at portal and email will be send to corresponding users 5. Mobile user can view his submitted forms on mobile application | No integration with middleware | 0 | [6 empty] | 0
26 | Cheque Book request | Yes |  | No | same as point 25 | same as point 25 | 0 | [6 empty] | 0
27 | Stop Cheque | Yes |  | No | Cheque can be in series as well as a single cheque middleware will send response chequewise accordingly | 1. Stop cheque request at middleware | 1 | [6 empty] | 1
28 | Block Cards | Yes |  | No | 1. Debit Cards 2. Prepaid Card 3. Credit Card | 1 Card status change request to middleware | 1 | [6 empty] | 1
29 | Listing of Offers | Yes | 19.12.2016: What is the integration point and hosting point This also needs explanation what kind of offers are referred to here. Are these card based, location based or otherwise. Please expand in detail | No | 23.12.2016: JSBL: Kazim (IT), backend portal requirement, to upload static images (total number of offers should not be limited to a number). These are general bank offerings | No integration required on middleware Enablement and diablement of offer will be avaibe on the backend portal and reodering | 0 | [6 empty] | 0
30 | Personalization Screen / User Information Screen (interface color change option for user) | Yes | Requirements need to be discussed in detail | No | 23.12.2016: JSBL: Kazim (IT), 2 parts. One control will be in the hands of the customer such as themes and background. Only on the application (not backend) | static colors will be decided at the time of development and will be availble for the user to change | 0 | [6 empty] | 0
31 | Reminders Alarms | Yes | What types of alarms are required and what are the hosting points? (i.e bill payment dates, location based, date and time based?) The type of integration will be determined based on this, and hence the cost if any. | No | 23.12.2016: JSBL: Kazim (IT), no integration required. Reminders according to date and time in conjunctions with payments | it will be a simple remider in the application stored on the server and delivered via push notification | 0 | [6 empty] | 0
32 | Offline Request Forms | Yes | We understand it will cover only 3-4 type of forms and Please provide detail i.e. Hosting and integration point/system. Is there any workflow required beyond this item since this is offline? | No | 23.12.2016: JSBL: Kazim (IT), there will more forms than 3-4 but JSBL don’t know the exact number. JSBL 10-15 forms. Integration will be required with the Workflow system in the future. Integration will be required with SMTP (Email Server). JSBL wants it to be configurable from the back end that offline forms can be mailed to the relevant POC | same as point 25 | 0 | [6 empty] | 0
33 | Online Request Forms | Yes | We understand it will cover only 3-4 type of forms and Please provide detail i.e. Hosting and integration point/system. | No | 23.12.2016: JSBL: Kazim (IT), integration with middleware. Such as account opening/estatement subscription | same as point 25 | 0 | [6 empty] | 0
34 | Customer Feedback | Yes |  | No | Application front end send email Backend bank portal user can access report of the feedbacks | no integration required with middleware | 0 | [6 empty] | 0
35 | Branch Hours Information | Yes | Detail Requirement is needed. | No | Application front end Backend bank portal user for configurations & management of new and existing branches | no integration required from middleware | 0 | [6 empty] | 0
36 | Product information | Yes | Q: Will an integration call be available for the same. Can you please explain the functionality that is required for this? What type of products are you referring to? | No | 23.12.2016: JSBL: Kazim (IT), static information no integration required. Product information will be an option in the menu or sub menu and where all product information is required. Will be uploaded from the backend portal | no integration required from middleware | 0 | [6 empty] | 0
37 | Smart Watch Notification | Yes | Our understanding is that this will cover Apple Watch, Moto 360, and Samsung Gear i.e. 3 OS's. | No | 23.12.2016: JSBL: Ainain: JSBL is ok with the 3 options listed on the right. | 0 | 0 | [6 empty] | 0
38 | Admin Portal: 1. Review Complaints/ Suggestions/ Complaint Registration 2. Enable/ Disable Features available on Mobile application 3. System Permissions 4. User Level Permissions 5. Block/ Unblock Users 6. Activity Logs 7. Offline request for new Account (All product) 8. Push notification | Yes | Basic Portal can be provide with the following features: 1. Review Complaints/Complaint Registration 2. System Permission 3. User Level Permission 4. Activity logs/Audit logs/Action Logs 5. Offline request for new Accounts. 6. Push Notifications 7. Enable/Disable Features | Yes | 1. Reordering of menu options 2. Change Menu Names 3. Enable/Disable a particular transaction 4. User Level role based permissions on admin portal 5. Activity logs of front end & back end users available seprately at admin portal 6. Positive and negative cases included 7. Permissions profile will be availble for the user (create & Tag) with maker checker concept 8. Admin portal can view & forcefully logout active session of an individual and multiple users | 0 | 0 | [6 empty] | 0
39 | Market Watch (Indices) 1) Live PSE market Status (Integration is PSE Feed) 2) Market Highlights 3) Live PSE Status Graph (TOP VOLUME) (ADVANCER/DECLINERS) (MY STOCK) | Development Required | We assume that Inov8 needs to integrate with a single system. Please confirm hosting & integration points. Bank will bear any additional cost associated with this development and integration. It is recommended that the Bank do away with this item | No | 23.12.2016: JSBL: Kazim: JSBL 2 different integration points. 1. LIVE PSE Kazim will get back to Inov8 but at this time the understanding this will be catered by through the middleware | 2 | 5 | [6 empty] | 5
40 | News(Breaking,National,Bullien,Forex) | Development Required | We assume that Inov8 needs to integrate with a single system. Please confirm hosting & integration points. Bank will bear any additional cost associated with this development and integration. It is recommended that the Bank do away with this item | No | 23.12.2016: JSBL: Kazim: JSBL 2 different integration points. 1. News and Feed Kazim will get back to Inov8 but at this time the understanding this will be catered by through the middleware | 2 | 5 | [6 empty] | 5
41 | Notifications Latest Promotions Location Based Advertisements JS News New App Updates | Yes | 1. Please provide types of Alarms 2. We assume that Inov8 will need to integrate with a single system. Please confirm hosting & integration points. 3. Bank will bear any additional cost associated with this development and integration. 4. Further we assume location based advertisement is city based advertisement | No | 23.12.2016: JSBL: Kazim: These are all push based notification from the backend portal There should be a notifications section in the application. And new app updates should be shown in a pop up upon login after updating the application | no integration required however there will be an option at admin portal to configure and push notifications based on profiling customer will receive notifications on app | 0 | [6 empty] | 0
42 | Customer Limits based on Profile | Yes | Detailed requirement is required | No (Only Wallet Limits are applicable) | this will be managed by the middleware | no integration required | 0 | [6 empty] | 0
43 | Banking products(lead generation) DEPOSIT PRODUCTS CARD PRODUCTS REMITTANCE SERVICES LOANS & RUNNING SERVICES | Yes | Detailed requirement is required We assume that these leads are offline and it would be simple information capturing and forwarded to a specific system of the bank for further handeling at their end. | No | 23.12.2016: JSBL: Kazim: Agreed same as point 25 | same as point 25 | 0 | [6 empty] | 0
44 | Financial graph | Yes | We asume that it will be showing graph of transactions initiated through the Mobile Banking application only. If not, please specify. | No | JSBL to share a view for display of the financial graph | 1 - view will be provided by jsbl | 4 | [6 empty] | 4
45 | - Scheduler module (view and Pay scheduled transactions) Utility Bill Payments | Yes | This will be handled at JS Bank middleware level for onward submission to Internet Banking (Nimbus / RDV will have to expose secheduler calls) | No | 23.12.2016: JSBL: Kazim: Facility available on middleware. Will be handled on middleware and more detailed discussion is required | 3 FT IBFT UBP | 4 | [6 empty] | 4
| - Date wise |  |  | No | [9 empty] | 0
| - Daily/Weekly/Monthly |  |  | No | [9 empty] | 0
| - Cyclic/Preodic |  |  | No | [9 empty] | 0
46 | Cardless cash withdrawals | Yes | This has to be implemented at JSBL middleware and ATM controller and ATM machines. On what system will the transaction origination happen? | Yes | 23.12.2016: JSBL: Kazim: Agreed, will be implemented on middleware first. Customer will enter desired amount with necessary information on Mobile app and a transaction will be send to middleware and will return a unique code, customer will receive a notification and sms OTP or ATM Pin based verification | 1 | 2 | [6 empty] | 2
47 | Splash / Brand Launch Screen | Yes |  | Yes | refer to point 29 & 30 | refer to point 29 & 30 | 0 | [6 empty] | 0
48 | Login with 2 Factor Authentication | Yes |  | Yes | User & Password authentication will be done by middleware and customer CNIC, Mobile Number & emaill will be returend to JSBL MB app and MB app will send OTP to that specific mobile number |  | 2 | [6 empty] | 2
49 | Account Summary | Yes |  | No | Transaction Initiation from: 1. Core Banking Account 2. Loan 3. TDR 4. Checking Accounts 5. Debit Card 6. Credit Card 7. Prepaid Card 8. BLB 9. JS Investment 10. JS Global | 10 A single call will be used to fetch multiple records and the details against each category | 7 | [6 empty] | 7
50 | Account Statement ( Mini ) | Yes |  | Yes | Transaction Initiation from: 1. Core Banking Account 2. Loan 3. TDR 4. Checking Accounts 5. Debit Card 6. Credit Card 7. Prepaid Card 8. BLB 9. JS Investment 10. JS Global | 10 A single call will be used to fetch last 10 transactions of selected accounts against each category to fetch | 7 | [6 empty] | 7
51 | Beneficiary Management | Yes |  | Yes | refer to point 14 & 15 | refer to point 14 & 15 | 0 | [6 empty] | 0
52 | Change Password | Yes |  | Yes | refer to point 13 | refer to point 13 | 0 | [6 empty] | 0
53 | Templates / Quick Pay | Yes |  | No | will be managed by MB platform Features: 1. Add 2. Update 3. Remove 4. Payment Transaction Covered: FT IBFT Prepaid Payment/Mobile Topup | No integration required | 0 | [6 empty] | 0
54 | FAQ & Terms and Condtions sections & Disclaimer | Yes |  | Yes | FAQ & Terms and Condtions sections & Disclaimer sections will be available on mobile app and Bank user can update and change the text from admin portal | No integration required | 0 | [6 empty] | 0
55 | Cheque Management ( Inquiry ) | Yes | Detail required and is integration dependant | No | 23.12.2016: JSBL: Kazim: Can be a single cheque inquiry and series inquiry Cheque can be in series as well as a single cheque middleware will send response chequewise accordingly | 1. Cheque inquiry request at middleware | 2 | [6 empty] | 2
56 | Card Management ( PIN Change, Information, Replacement , Blocking and Limit Management ) | Yes | Dependant on integration | As part of debit card mangement module | Refer to 13, 28 & 49 Hierarchy 1. Limit Profile ID a. Multiple Transaction has multiple fields (Complete Grid) b. Limits of Transactions Customer can change profiles. | 2 Limit Fetch Limit Set | 3 | [6 empty] | 3
57 | Debit/Prepaid/Credit Customer registration and transactions support | Yes | Dependant on integration | L0/L1 Account opening is available through App. | 23.12.2016: JSBL: Kazim: online registration process for mobile banking. Customer profiling on the basis of input for registration. In case the FT's need to be segregated on the middleware as per customer resgistration on the basis of input, Inov8 will cater the same Debit /Prepaid/ Credit Cards: As per existing Debit cards onboarding process there is a change only link will not be sent to the customer Customer profiling based on the onboarding instrument | Needs to be finalized by JSBL | 0 | [6 empty] | 0
58 | Complaints and Suggestions | Yes |  | No | refer to pint 34 | refer to pint 34 | 0 | [6 empty] | 0
59 | Personal Financial Management | Yes | Is there any diffence between financial graph point 44 and this one | No | 23.12.2016: JSBL: Kazim: Customer can set his goals and targets and all of the items are interlinked with financial graph. Tables will be exposed by JSBL | Needs to be finalized by JSBL | 0 | [6 empty] | 0
60 | Proactive Alerts on certain conditions set by the user | Yes | Please provide details | No | 23.12.2016: JSBL: Inov8 JSBL to identify the number of event for such alerts. Min & Max balance alerts Loan due date TDR maturity date will be handeled through day end scheduler with in mobile banking - no separate integration required Admin portal have rights to enable and disable alerts on global level | no integration required | 0 | [6 empty] | 0
61 | User Access Analytics | Yes | Please provide details | No | 23.12.2016: JSBL: Kazim requires that how many click on MENU, how many times he clicked on IBFT. Managed within MB platform and backend user will have the report access covering OS, device details, user and ip address and menu used | no integration required | 0 | [6 empty] | 0
62 | Dynamic Banners and Ads | Yes | Available in Mobile Banking | No | 23.12.2016: JSBL: JSBL to provide the rules of dynamic banners and ads linked with point 29 and rules for displaying the banners as per targetted market 1. Location based 2. Balance 3. Profile/Product 4. Transaction Volume/Count 5. Transaction Type | no integration required | 0 | [6 empty] | 0
63 | Web Chat | Development Required | We assume that the Webchat will be hosted at JS Bank's CRM and the MoBank application will only be the frontend for the user. Kindly confirm. | No | 23.12.2016: JSBL: JSBL agrees to Inov8 understanding. | Needs to be finalized by JSBL | 0 | [6 empty] | 0
64 | PADSS compliant | Yes |  |  | PCIDSS compliant | NA | 0 | [6 empty] | 0
65 | Dashboards | Yes | Available with us for portal but detailed requirement is required | No | Will be available at backend on admin portal | no integration required | 0 | [6 empty] | 0
66 | Quick Links | Yes |  | No | out of scope due to IOS limitation | NA | 0 | [6 empty] | 0
67 | Most frequently used features visible at all times | Yes | This will be a single button which will host the top 3 used features upon being clicked. Please confirm | No | 23.12.2016: JSBL: JSBL agrees to Inov8 understanding. Available only at mobile app | no integration required | 0 | [6 empty] | 0
68 | Wizard based interfacing for step by step user action | Yes | We assume that transaction wise tutorial, it's graphics, production, editing, music etc. will be created via an agency by JSBL. It will then be uploaded on Youtube by the bank and the application will be a frontend for the user to view it. This will be done per transaction or feature. | No | 23.12.2016: JSBL: Upon first time login or using a feature for the first time then the customer should be able to see hints and tips. JSBL to provide informaion for hints/tips. Wizard will be covered at the time of FS Hint/Tips should be displayed on first time usage and user can set on/off at the time of registration and in seetings at later stage | no integration required | 0 | [6 empty] | 0
69 | Loan Calculator | Yes | Detailed requirement is required | No | Markup rate will be decided at the time of FS | no integration required | 0 | [6 empty] | 0
70 | Tutorials | Yes | Please see point 68 above. | No | 23.12.2016: JSBL: JSBL agrees to Inov8 understanding written in point 68. videos URL will be uploaded by bank admin portal customer app will display accordingly | no integration required | 0 | [6 empty] | 0
71 | BLB account pulls amount from core account | Yes | N/A | Yes | refer to point 1 | refer to point 1 | 0 | [6 empty] | 0
72 | Forgot/Reset Internet Password | Yes |  |  | Customer can reset PW by inputting his anwers to the secret question set by himself at the time of registration | Needs to be finalized by JSBL | 0 | [6 empty] | 0
73 | Falconpay registerarion process | Yes |  |  | onboarding and authentication needs to be finalized | Needs to be finalized by JSBL 1 Self Linkage Card Account relationship inquiry Multiple accounts can be return | 2 | [6 empty] | 2

## Transactions List
Status Legend:
| Yes | Option Readily Available i.e. No development Required
| NO | Option not available and cannot be provided
| Development | Option will be provided after development
S.No. | Existing Backend Transaction List | Status | Additional Comments
All these features are available with Inov8 and they would require an integration with the relevant system at JSBL. They are also dependant on what calls will be available to Inov8 from JSBL integration.
1 | Account Full Statetment | Yes
2 | Title Fetch | Yes
3 | UBPS Customer Registration | Yes
4 | UBPS Customer Un register | Yes
5 | Autheticate Customer | Yes
6 | Beneficiary Account List | Yes
7 | Beneficiary Account List PPC | Yes
8 | Beneficiary maintenance | Yes
9 | Bill Inquiry | Yes
10 | Card Details | Yes
11 | Card Status Change | Yes
12 | Change Password | Yes
13 | Check UserId Availability | Yes
14 | Checking Account Summary | Yes
15 | CNIC validation | Yes
16 | Funds Transfer | Yes
17 | Generate FPIN | Yes
18 | Get Card List | Yes
19 | Get Card List PPC | Yes
20 | Get Password | Yes
21 | Get Registered Consumers | Yes
22 | IBFT | Yes
23 | IBFT Beneficiary Account List | Yes
24 | IBFT Beneficiary Account List PPC | Yes
25 | IBFT Beneficiary maintenance | Yes
26 | IBFT Title Fetch | Yes
27 | Instrument Status | Yes
28 | Loan Account Details | Yes
29 | Loan Account Summary | Yes
30 | Mini Statement | Yes
31 | PanPin Verification | Yes
32 | SI Bill Payment | Yes
33 | SI Funds Transfer | Yes
34 | SI IBFT | Yes
35 | SI Mini Statement | Yes
36 | Stop Cheque Payment | Yes
37 | Store Registration Data | Yes
38 | TDR Account Details | Yes
39 | TDR Account Summary | Yes
40 | Transaction Fee Inquiry | Yes
41 | Utility Bill Payment | Yes
42 | Beneficiary maintenance PPC | Yes
43 | Card Details PPC | Yes
44 | Donation Funds Transfer | Yes
45 | Donation Title FETCH | Yes
46 | Prepaid Card Recharge | Yes
47 | Cheque Book Request | Yes
48 | Paper Statement Request | Yes
49 | Pay Order Request | Yes
50 | Demand Draft Request | Yes
51 | Apply for VISA Debit Card | Yes
52 | Request Form | Yes